## Use Case Support
Use Case | Current Capability | What Remains To Be Built
1.1 Create a Reseller Partner Tenant | Partially supported: the backend supports reseller partner CRUD and customer tenants can be linked to a reseller, but there is no dedicated reseller management UI. | Build a reseller-facing or super-admin UI for creating reseller tenants, assigning initial reseller admins, and managing the reseller record end to end.
1.2 Assign Reseller Portfolio Scope | Partially supported: tenants carry a reseller reference and admin scopes can restrict access by reseller, but there is no explicit portfolio assignment workflow. | Add portfolio assignment and reassignment flows, reseller portfolio views, and UI controls for linking or unlinking tenants from a reseller.
1.3 Grant Reseller Admin Capabilities | Partially supported: the admin model supports roles, permissions, and reseller or tenant scopes, but the dedicated admins area is still a placeholder in the frontend. | Finish the admin-management UI with reseller-specific presets, permission templates, and delegation guardrails for reseller admins.
1.4 Initialize Reseller Defaults | Not supported: the app uses some generic form defaults, but it has no reseller default or template system. | Add reseller-level defaults for portal config, runtime settings, activation templates, and inherited onboarding presets for new customer tenants.
2.1 Create Customer Tenant | Supported: the activation workflow and tenant API can create draft or onboarding tenants with profile metadata. | Polish reseller-specific entry points and stronger validation, but the core create-tenant capability is already in place.
2.2 Configure LLM Provider | Supported: tenant LLM configuration supports customer-managed and platform-managed credentials, provider selection, model selection, and vault-backed secrets. | Expand provider-specific UX and add richer validation rules or provider-specific setup guidance if needed.
2.3 Validate LLM Configuration | Partially supported: validation exists, but it mainly checks required fields and whether the referenced secret can be resolved from the vault. | Add live provider connectivity tests, model availability checks, and more realistic request-level validation before activation.
2.4 Define Runtime Settings | Supported: tenant runtime settings can be viewed and updated for enforcement, retention, reporting, exports, and feature flags. | Add more policy coverage only if the product needs additional runtime controls beyond the current fields.
2.5 Create Groups | Supported: groups can be created, listed, and updated in both the backend and frontend. | Add richer hierarchy editing, drag-and-drop organization, and group detail analytics if deeper group administration is needed.
2.6 Import Users | Partially supported: users can be added and invited one at a time, but there is no bulk import workflow. | Build CSV or spreadsheet upload, validation, preview, and bulk invitation or membership creation flows.
2.7 Assign Admins | Partially supported: admins can be created with permissions and scopes, including during activation, but the standalone admins page is not finished. | Complete the admins management screens for search, edit, revoke, and audit-friendly administration outside the activation flow.
2.8 Monitor Onboarding | Supported: onboarding status is tracked and surfaced on the activation landing page, dashboard, and organization detail views. | Add richer milestone history, blocking reason summaries, and SLA-style reminders if onboarding operations need more depth.
2.9 Activate Tenant | Supported: the tenant can be activated once readiness checks pass, and the backend blocks activation when required steps are incomplete. | Add optional activation confirmations, activation logs, and richer post-activation workflows if needed.
3.1 Manage Users | Supported: the app lists users, supports membership updates, and includes lifecycle actions such as deactivate, reinvite, and delete. | Add deeper user detail pages, bulk actions, and stronger search or filtering if operators need a fuller user-admin console.
3.2 Manage Groups | Supported: the app supports group listing, filtering, creation, and updates. | Add group detail pages, membership editing, and hierarchy tooling to make group management more complete.
3.3 Manage Admin Roles | Partially supported: the backend fully models admin roles, scopes, and permissions, but the primary frontend experience is still incomplete. | Ship the full admins UI and add workflows for reviewing delegated privileges, revoking access, and editing scopes safely.
4.1 View Dashboard | Supported: there is a real dashboard with KPIs, trends, alerts, and onboarding snapshots. | Continue refining the data model and visual polish, but the core dashboard capability exists today.
4.2 Analyze Prompt Quality | Partially supported: the app exposes average improvement and trend metrics, but it does not yet offer a dedicated prompt-quality analysis workflow. | Add deeper quality drill-downs, cohort comparisons, prompt-quality slices, and analyst-oriented reporting views.
4.3 Identify Behavior Gaps | Partially supported: the dashboard and reporting surface some issues indirectly through alerts and improvement metrics, but there is no dedicated behavior-gap analysis tool. | Build explicit gap-detection views, exception reports, and recommended follow-up actions for analysts or admins.
4.4 Generate Reports | Partially supported: the backend can run report payloads, but the frontend reporting page is still a placeholder. | Complete the report-builder UI, saved report flows, filtering UX, and report navigation.
4.5 Export Reports | Partially supported: report export jobs exist and CSV export is implemented, but there is no completed exports UI and PDF export is not implemented. | Finish the exports screen, download history, job status management, and non-CSV output formats such as PDF.
5.1 Manage Portfolio | Partially supported: organizations can be viewed across scope and tied to resellers, but there is no dedicated reseller portfolio workspace. | Add portfolio dashboards, reseller-level filtering, cross-tenant actions, and a proper reseller portfolio management experience.
5.2 Monitor Portfolio Health | Partially supported: health signals such as onboarding gaps and invalid LLM configs are surfaced, but there is no full portfolio-health console. | Build reseller-focused health dashboards, inactive or misconfigured tenant queues, and follow-up workflows.
6.1 Investigate Issues | Partially supported: operators can inspect tenant details, onboarding state, users, runtime config, and LLM validation status, but there is no dedicated operations workbench. | Build the operations screens for investigation trails, issue queues, deeper diagnostics, and cross-tenant troubleshooting.
6.2 Audit Actions | Partially supported: audit entries are written and exposed by API, but there is no finished audit-log frontend screen. | Add an audit log UI with filtering, drill-down details, and export or retention tooling for compliance use cases.
7.1 Reassign Tenant | Not supported: there is no workflow or endpoint for moving a tenant from one reseller to another. | Implement tenant transfer rules, audit-safe reassignment APIs, UI confirmations, and downstream scope refresh handling.
7.2 Override Activation | Not supported: activation is intentionally blocked until readiness checks succeed, and there is no override path. | Add a super-admin override workflow with reason capture, audit logging, and visible risk warnings.
7.3 Partial Onboarding | Supported: the workflow supports draft and in-progress onboarding states before all requirements are met. | Add more explicit paused or deferred states if the team wants to distinguish partial onboarding from active setup work.
7.4 Service Mode Activation | Partially supported: service mode is captured on the tenant profile, but it does not drive a distinct activation path or ruleset. | Implement service-mode-specific activation logic, requirements, and UI behavior for phased rollouts or minimal service launches.
8.1 Scoped Reporting | Supported: permissions and scopes are enforced in reporting APIs, and dashboard or report queries can be limited to the current scope. | Add richer scoped-reporting UX, especially on the unfinished reporting pages, but the core access-control behavior exists.
8.2 Scoped Investigation | Partially supported: scope enforcement exists across tenant, user, group, admin, onboarding, and report access, but investigation tooling itself is still shallow. | Build dedicated scoped investigation screens and richer support workflows while preserving the existing scope checks.